## anusree
Date | WFD | EOD | Note
2026-02-11 | Project planning & requirement analysis | Defined app flow and UI plan | -
2026-02-12 | Flutter setup | Created project and structure | -
2026-02-13 | UI design | Built login & home screens | -
2026-02-14 | Student login UI | Completed student login screen | -
2026-02-15 | Driver login UI | Completed driver login screen | -
2026-02-16 | API integration planning | Prepared for backend connection | -
2026-02-17 | Login API integration | Connected frontend with backend | -
2026-02-18 | Debugging login issues | Fixed API errors | -
2026-02-19 | Tracking UI | Designed map UI | In progress
2026-02-20 | Map integration | Integrated Google Maps | -
2026-02-21 | Location display | Location shown but inaccurate | Issue
2026-02-22 | Debugging tracking UI | Tried improving display | Ongoing
2026-02-23 | Testing UI | Found delay issues | -
2026-02-24 | GitHub upload | Uploaded frontend code | -
2026-02-25 | Team merge | Updated latest code | -
2026-02-26 | UI improvements | Enhanced UI | -
2026-02-27 | Bug fixing | Fixed UI bugs | -
2026-02-28 | Testing | UI stable | Tracking issue persists
2026-03-01 | Emulator testing | Fixed connection issues | -
2026-03-02 | Build attempt | Build failed | -
2026-03-03 | Debugging build | Worked on errors | -
2026-03-04 | Fix build issues | Partial fix done | -
2026-03-05 | UI enhancement | Improved UX | -
2026-03-06 | Navigation improvement | Optimized flow | -
2026-03-07 | Testing | Verified modules | -
2026-03-08 | Documentation | Started writing docs | -
2026-03-09 | Resume update | Added project | -
2026-03-10 | Bug fixing | Minor fixes | -
2026-03-11 | Tracking debug | UI sync issue | Ongoing
2026-03-12 | Review prep | Prepared demo | -
2026-03-13 | Review meeting | Presented frontend | -
14–22/03/2026 | Semester exams | No work done | Academic priority
2026-03-23 | Resume work | Updated GitHub links | -
2026-03-24 | UI polish | Improved design | -
2026-03-25 | Minor fixes | Fixed bugs | -
2026-03-26 | Testing | UI stable | -
2026-03-27 | Validation | Checked flow | -
2026-03-28 | Final UI check | Ready frontend | Backend issue pending

## supritha
Date | WFD | EOD | Note
2026-02-11 | Project planning & backend requirement analysis | Defined API structure and flow | -
2026-02-12 | Backend setup | Initialized server and environment | -
2026-02-13 | Database design | Created database schema | -
2026-02-14 | Authentication API | Implemented login APIs | -
2026-02-15 | Driver module API | Added driver-related endpoints | -
2026-02-16 | API testing | Verified API responses | -
2026-02-17 | Frontend integration support | Assisted in connecting APIs | -
2026-02-18 | Debugging authentication | Fixed API errors | -
2026-02-19 | GPS tracking logic | Implemented location tracking | In progress
2026-02-20 | Location API development | Created API for location updates | -
2026-02-21 | Tracking testing | Detected inaccurate location data | Issue
2026-02-22 | Debugging tracking | Investigating tracking inconsistency | Ongoing
2026-02-23 | API testing | Observed delay in updates | -
2026-02-24 | GitHub upload | Uploaded backend code | -
2026-02-25 | Code merge | Synced team updates | -
2026-02-26 | API optimization | Improved performance | -
2026-02-27 | Debugging | Tracking delay persists | -
2026-02-28 | Testing | Partial improvements | Tracking issue persists
2026-03-01 | Device testing | Verified API responses | -
2026-03-02 | Build support | Assisted in resolving build issues | -
2026-03-03 | Debugging | Fixed backend errors | -
2026-03-04 | Issue fixing | Improved backend stability | -
2026-03-05 | Optimization | Enhanced API performance | -
2026-03-06 | Feature refinement | Improved tracking logic | -
2026-03-07 | Testing | Verified backend modules | -
2026-03-08 | Documentation | Prepared API documentation | -
2026-03-09 | Updates | Added improvements | -
2026-03-10 | Bug fixing | Fixed minor backend issues | -
2026-03-11 | Tracking debugging | Worked on sync issues | Ongoing
2026-03-12 | Review preparation | Prepared backend explanation | -
2026-03-13 | Project review meeting | Presented backend module | -
2026-03-14 | Semester examinations | No project work done | Academic priority
2026-03-15 | Semester examinations | No project work done | Academic priority
2026-03-16 | Semester examinations | No project work done | Academic priority
2026-03-17 | Semester examinations | No project work done | Academic priority
2026-03-18 | Semester examinations | No project work done | Academic priority
2026-03-19 | Semester examinations | No project work done | Academic priority
2026-03-20 | Semester examinations | No project work done | Academic priority
2026-03-21 | Semester examinations | No project work done | Academic priority
2026-03-22 | Semester examinations | No project work done | Academic priority
2026-03-23 | Debugging tracking | Analyzed issue deeply | -
2026-03-24 | Fix attempts | Tried solutions for tracking | -
2026-03-25 | API updates | Improved synchronization | -
2026-03-26 | Testing | Issue still inconsistent | -
2026-03-27 | Debugging | Tracking issue persists | -
2026-03-28 | Current work | Fixing tracking issue | In progress

## rakshitha
Date | WFD | EOD | Note
2026-02-11 | Requirement study | Understood system workflow | -
2026-02-12 | Environment setup | Prepared testing tools | -
2026-02-13 | UI flow testing | Verified screen navigation | -
2026-02-14 | Login module testing | Tested student login | -
2026-02-15 | Driver module testing | Tested driver login | -
2026-02-16 | API testing | Validated backend responses | -
2026-02-17 | Integration testing | Verified frontend-backend connection | -
2026-02-18 | Bug reporting | Reported login issues | -
2026-02-19 | Tracking testing | Tested GPS tracking | Issue
2026-02-20 | Map testing | Verified map functionality | -
2026-02-21 | Location accuracy testing | Found incorrect location data | Issue
2026-02-22 | Backend support | Helped in debugging tracking | Ongoing
2026-02-23 | Testing | Observed delay issues | -
2026-02-24 | Repository verification | Checked GitHub updates | -
2026-02-25 | Merge testing | Verified integrated code | -
2026-02-26 | Performance testing | Checked app performance | -
2026-02-27 | Bug tracking | Logged issues | -
2026-02-28 | Testing | Issues still present | Tracking issue persists
2026-03-01 | Device testing | Tested on emulator/device | -
2026-03-02 | Build testing | Identified build issues | -
2026-03-03 | Debug support | Assisted in fixing backend bugs | -
2026-03-04 | Retesting | Verified fixes | -
2026-03-05 | UI testing | Checked user experience | -
2026-03-06 | Flow testing | Verified navigation flow | -
2026-03-07 | Testing | Stable modules verified | -
2026-03-08 | Documentation | Prepared test reports | -
2026-03-09 | Feedback updates | Added improvements | -
2026-03-10 | Bug validation | Verified fixes | -
2026-03-11 | Tracking testing | Issue still persists | -
2026-03-12 | Review preparation | Prepared testing report | -
2026-03-13 | Project review meeting | Presented testing results | -
2026-03-14 | Semester examinations | No project work done | Academic priority
2026-03-15 | Semester examinations | No project work done | Academic priority
2026-03-16 | Semester examinations | No project work done | Academic priority
2026-03-17 | Semester examinations | No project work done | Academic priority
2026-03-18 | Semester examinations | No project work done | Academic priority
2026-03-19 | Semester examinations | No project work done | Academic priority
2026-03-20 | Semester examinations | No project work done | Academic priority
2026-03-21 | Semester examinations | No project work done | Academic priority
2026-03-22 | Semester examinations | No project work done | Academic priority
2026-03-23 | Testing | Retested tracking feature | -
2026-03-24 | Backend support | Helped resolve bugs | -
2026-03-25 | Validation | Checked fixes | -
2026-03-26 | Testing | Issue still inconsistent | -
2026-03-27 | Testing | Verified modules | -
2026-03-28 | Current testing | Ongoing testing & bug fixing | In progress